DO NOT WRITE ON TEST

PROJECT MANAGEMENT

CONCEPTS

(593)

# —Post-secondary—

NATIONAL 2020

TOTAL POINTS	___________ (100)

Failure to adhere to any of the following rules will result in disqualification:

- Contestant must hand in this test booklet and all printouts. Failure to do so will result in disqualification.

- No equipment, supplies, or materials other than those specified for this event are allowed in the testing area.  No previous BPA tests and/or sample tests or facsimile (handwritten, photocopied, or keyed) are allowed in the testing area.

- Electronic devices will be monitored according to ACT standards.

No more than sixty (60) minutes testing time

Property of Business Professionals of America.

May be reproduced only for use in the Business Professionals of America

Workplace Skills Assessment Program competition.

Identify the letter of the choice that best completes the statement or answers the question.

- Which of the following is an organizational structure that is characterized by multiple projects being worked on at any one time, with these projects varying in size and complexity?

- autonomous

- functional

- matrix

- project

- All of the following are vital to project success, EXCEPT

- creating deliverables that include all required features.

- completing the project on schedule and on budget.

- providing outputs that please the project’s customers.

- involving only important key stakeholders.

- Which of the following statements regarding project life cycles is most accurate?

- All research and development projects use the same four-stage project life cycle model.

- A company uses the same project life cycle for all project types.

- Many different project life cycle models are used for different types of projects.

- Project life cycles are very similar regardless of the industry.

- The following are reasons to conduct a project budget analysis EXCEPT to

- identify project mismanagement.

- enable estimators to make more accurate estimates.

- enable estimators to evaluate estimate variances.

- allow more efficient scheduling.

- The scheduling process

- is a random list of events that should occur during project completion.

- is a management tool to run a project.

- is a timeline of events that should occur for a project to be completed.

- assigns items to a time duration that follows the sequence of project activities.

- All of the following occur during the project control function phase of scheduling, EXCEPT

- implementing corrective action.

- implementing corrective planning.

- documenting production inefficiencies.

- documenting product deviations.

- A project owner requests a change order with added costs to the contractor of $2,500 in labor and $1,000 in overhead. The contractor will save $1,250 in labor and $250 in overhead. The original bill included a 5% markup. What amount must be billed to the change order?

- $1,050

- $1,575

- $2,100

- $3,500

- Project resource costs typically include all the following EXCEPT

- fees for subcontractors performing project tasks.

- fees for renting facilities for the project.

- salaries of members of the project team.

- costs for equipment that extends beyond the project time.

- A project’s acceptance criteria

- summarizes the need and justification for the project.

- states the quantitative criteria expected for the products to be accomplished.

- frees all parties from liabilities arising from events beyond their control.

- is concise and creates a vision for the project’s end result.

- A scope document helps establish

- a request for proposal.

- a common understanding of the project's scope among all stakeholders.

- the contact between the contractor and the customer.

- the risk management plan.

- A project’s change control system defines

- how changes will be analyzed, approved or declined, and managed.

- acceptable risks for the project.

- how acceptance criteria are evaluated.

- how the quality plan is applied and evaluated.

- The ________ shows the individuals associated with each work item in the work breakdown structure, and the work items associated with each individual.

- responsibility assignment matrix

- plan cost estimate

- schedule control plan

- project scope document

- Which of the following correctly identifies three possible time estimates for projects that contain a high degree of uncertainty about the estimated durations for activities?

- original, practical, and a most-likely estimate

- optimistic, pessimistic, and a most-likely estimate.

- optimistic, pessimistic, and realistic estimate.

- opportunity, pragmatic, and realistic estimate.

- Calculate the earliest start for Task D if one of its predecessors, Task A, finishes on day 2, its other predecessor, Task C, finishes on day 4, and the duration of Task D is 6 days.

- day 6

- day 5

- day 4

- day 3

- A project’s total completion time is 30 days. Task A is planned to take 7 days. Task B is planned to take 5 days. Task C is planned to take 8 days. The tasks have a serial relationship. Task A takes 10 days to be completed instead of 7 days. How much slack does the project have now that Task A is finished?

- negative 7 days slack

- positive 13 days slack

- positive 20 days slack

- positive 7 days slack

- The project control process includes all of the following EXCEPT

- scope verification.

- performance reporting.

- activity sequencing.

- risk monitoring and control.

- Calculate the latest start for Task B if one of its successors, Task C, has a latest start on day 10, its other successor, Task D, has a latest start on day 10, and the duration of Task B is 2 days.

- day 18

- day 8

- day 12

- cannot be calculated based upon information given

- ______________ is the sum of the project budget for the activities accomplished to date.

- aggregated budgeted cost (ABC)

- cumulative budgeted value (CBV)

- cumulative actual cost (CAC)

- cumulative earned value (CEV)

- A cost performance index (CPI) measures the financial effectiveness and efficiency of a project. If the earned value (EV) is greater than the actual costs (AC), then the

- CPI is greater than 1.0.

- CPI is less than 1.0.

- project is under budget and behind schedule.

- project is over budget but ahead of schedule.

- If the project’s cost performance index (CPI) is greater than 1.0 and schedule performance index (SPI) is less than 1.0, the project is

- under budget but behind schedule

- under budget and ahead of schedule

- over budget but ahead of schedule

- over budget but behind schedule

- Calculate the cost variance (CV) for a project that has a total budgeted cost (TBC) = $50,000, earned value (CEV) = $25,000, and actual cost (CAC) = $20,000.

- CV = - $25,000

- CV = - $5,000

- CV = $5,000

- CV = $25,000

- Calculate the cost performance index (CPI) for a project that has a total budgeted cost (TBC) = $50,000, cumulative earned value (CEV) = $20,000, cumulative actual cost (CAC) = $16,000, and cumulative budget cost (CBC) = $17,500.

- CPI = 1.25

- CPI = 0.72

- CPI = 1.07

- CPI = 0.8

- During this stage of team development, team members begin to test the limits and flexibility of the project manager and the ground rules.

- forming

- norming

- storming

- performing

- _____________________ are all considered destructive team roles.

- Blocker, dominator, and information seeker.

- Dominator, recognition seeker, and initiator.

- Aggressor, initiator, and withdrawer.

- Withdrawer, dominator and recognition seeker.

- Which plan defines the generation and distribution of project documents among project stakeholders throughout the project?

- project distribution plan

- project communication plan

- project revision plan

- project scope plan

- The most common types of organizational structures are:

- functional, project, and matrix

- progressive, linear, and matrix

- framework, product, and matrix

- functional, autonomous, and management

- A _________ organizational structure allows for fast response upon problem identification with reporting relationships operating as a grid rather than a traditional hierarchy.

- functional

- project

- matrix

- autonomous

- Which project document contains the description, owner, source, priority, and status of product requirements?

- requirements management plan

- requirements traceability matrix

- scope management plan

- scope change control

- The following table includes an activity list with the duration and predecessor for a series of project activities. What is the duration of the critical path?

- 9

- 11

- 13

- 14

- A project manager is conducting the initial process of identifying stakeholders for a new project and has just compiled a list of potential stakeholders' names. What is the next step?

- close procurements

- conduct stakeholder analysis

- invite potential stakeholders to a kick-off meeting

- develop the risk register

- The project manager is preparing to create the new year’s budget and plans to review projects that were started in the past three (3) years but were put on hold for various reasons. Which one of the following should NOT be considered (will not impact) making future project decisions?

- earned value

- planned value

- fixed cost

- sunk cost

- Using the illustration below of a project network activity node, what is the total float of activity D?

- 2

- 5

- 16

- 18

- Which of the following would a project manager use to create a graphic representation of three dimensions (proximity, detectability, and impact value)?

- a RACI chart

- a Gantt Chart

- a bubble chart

- a bar chart

- Which of the following would best highlight identified activities that may create a delay in the overall project schedule?

- activity attributes

- project network diagrams

- SWOT analysis

- project calendars

- Your construction project was damaged by an earthquake. Your contractor says that he cannot fulfill the terms of the contract due to a specific clause you both signed. He is referring to the

- force majeure clause.

- fixed price clause.

- contract obligation terms.

- conflict resolution contract.

- You are trying to establish a cost performance baseline for your project in determine budget process. You can use the following tool and techniques EXCEPT:

- cost aggregation

- bottom-up estimating

- expert judgment

- historical relationships

- The project manager has prepared the following chart to review the status of a project that will be completed in five phases. Based on the information provided, calculate the earned value (EV) of the project?

| Task | Start Date | End Date | Duration (Days) | Planned Value | Actual Cost | Percent Complete |
| --- | --- | --- | --- | --- | --- | --- |
| Define | 3/1 | 3/31 | 30 | $1,750 | $1,950 | 100% |
| Measure | 4/1 | 4/30 | 29 | $2,250 | $2,150 | 100% |
| Analyze | 5/1 | 5/31 | 30 | $5,000 | $3,900 | 75% |
| Improve | 6/1 | 6/30 | 29 | $6,000 | $0 | 0% |
| Control | 7/1 | 7/31 | 30 | $1,500 | $0 | 0% |

- $7,750

- $7,850

- $15,250

- $3,950

- Calculate the schedule performance index (SPI) for a project reporting $2,800 earned value (EV), $2,000 actual cost (AC), and $3,500 planned value (PV).

- 1.85

- 1.25

- 0.90

- 0.80

- According to Herzberg’s Theory, all of the following are hygiene factors EXCEPT:

- salary

- personal life

- professional growth

- status

- A current project has $300 earned value (EV), $250 actual cost, $300 planned value (PV) and $1,500 original project budget. Assuming the project will continue to spend money at the same rate, what is the project’s estimate at completion (EAC)?

- $950

- $1,500

- $650

- $1,250

- Unexpected transportation and logistic issues have negatively impacted your cost and schedule estimates and invalidated your original estimated predictions. Calculate the updated estimate at completion (EAC) based on the following information.

BAC = $ 350,000

AC = $120,000

EV = $180,000

ETC = $150,000

CPI = 1.2

- $300,000

- $270,000

- $200,000

- $330,000

- _________ involves selecting the project team members who are the best qualified to perform each task and then empowering them to accomplish the expected results for his or her area of responsibility.

- Retainment

- Facilitation

- Detainment

- Delegation

- All of the following statements are true EXCEPT

- Portfolios are collections of projects and programs.

- Portfolios are managed as a group to achieve strategic business objectives

- Programs are collections of projects, portfolios and sub-portfolios.

- A portfolio performance plan is a guideline to identify portfolios and sub-portfolios.

- A ___________ is a structured, independent review to determine if the intended execution of project activities will comply with project and organizational policies, processes, and procedures.

- quality audit

- reject screening

- risk assessment

- inspection

- Which statement below regarding conflicts is true?

- Conflict resolution should focus on the people involved, not the issues.

- Conflict should always be resolved in private, not in the team environment.

- Conflicts should be resolved in a constructive and timely manner.

- Conflicts should never arise in a dynamic team environment.

- Which of the following techniques is used to show the effects of changing one or more variables on an outcome?

- Monte Carlo analysis

- sensitivity analysis

- Delphi analysis

- decision tree analysis

- Which of the following has become increasingly important with the growth of virtual team environments?

- risk management plans

- network diagram control limits

- communication planning

- daily phone conferences

- Which of the following is generally not considered an element of active listening?

- interrupting when appropriate

- asking questions to gain understanding

- maintaining comfortable eye contact

- remaining open minded

- Which of the following is least likely to be included as a key stakeholder for your project?

- project team

- project manager

- customer

- media representatives

- Project managers are traditionally assigned to a project

- as soon as the project is authorized.

- at any time during the project life cycle.

- if conflict occurs between project team members.

- following approval of the staffing management plan.